## Misc
Category | Sub_category | Content/Question | Note/Answer
|  | Does Pro*C/C++ generate calls to the Oracle Call Interface (OCI)? | No. Pro*C/C++ generates data structures, and calls to its runtime library: SQLLIB (libsql.a in UNIX). "

## ProC vs OCI
OCI

## Estimation
Assumption and question
- For last time development, the data for DB initialization is prepared as .ora data file. For this time HiRDB, is the corresponding data file prepared by HiICS or not.
For this time development
-
Pro*C vs OCI
|  | Pro*C |  |  |  | OCI
| Advantage | - Fast to catchup and development |  |  |  | - Take time to prepare initialization
- Easy to port to other environments, because almost every dbms support embedded SQL. So that with small change, the Pro*C file can be re-used with another dbms
|  | - Pro*C is easier to develop, but when SQL is changed. Pro*C program is also need to be changed |  |  |  | - OCI is diffult to develop than Pro*C, but it take SQL as input
Previous system's information
1227 text files.
1163 unique files.
575 files ignored.
| Language | Files | Blank | Comment | Code
| C | 441 | 17425 | 47996 | 118406
| SQL | 57 | 1077 | 198 | 19893
| C/C++ Header | 111 | 2577 | 8138 | 13204
| make | 117 | 2163 | 248 | 8946
| Visual Basic | 116 | 0 | 0 | 3599
| DOS Batch | 116 | 6 | 0 | 1781
| Bourne Shell | 6 | 34 | 258 | 720
| SUM | 964 | 23282 | 56838 | 166549
Re-usable part
Pro*C

## Overview
ID | Category | Sub-Category | Status | Content | PIC | Note | Know-how
- | Scope | Out_of_scope | - | Car Location server will not store movie data. It will be handled by separated system which repsonse for Video Streaming. | Other team
- | Scope | In_scope | - | Car Location server will store received image from Car, PSD device to FTP server, and provide path to corresponding system | GCS
- | Scope | Main functional of Car Location system | - | - PLH 災害機能 - PLG 統計機能 - PLF 業務制御 - PLE メンテナンス - PLD 外部連携 - PLC 映像連携 - PLB 画像連携 - PLA 動態管理機能 | GCS | - For each functional, will have all following list of document to design for it. + GCS onsite team will handle mainly PLA functional - For detail information for each functional, it can be checked from list of AA - SOA (Business Process) document - Please refer to functional_list sheet for more detail
- | Specification | Non-functional requirement | DONE | Non-functional requirement for this time development - RP11_02_01_制約条件一覧表.pdf - RP04_02_01_評価指標定義表.pdf | HiICS/GCS | - HiICS will responsible for creating design document satisfy required non-functional requirement - GCS will responsible for implementing system satisfy required non-functional requirement
- | Specification | Reference | DONE | Naming convention definition: 'HI-GB56_ネーミング基準書.doc | HiICS
- | Specification | Reference | DONE | Message convetion HI-JB62_メッセージ基準書.doc | HiICS
AA | Design Specs | Input | In-Progress | アプリケーション実装方式設計 Application Implement Method Design | HiCS
AA02-1 | Design Specs | Input | In-Progress | アプリケーション処理方式設計書【AA02-01#01】 Application Processing Method Design | HiCS | - Nakaoka-san will create this document for whole system, each team will check created document to see whether it's OK for corresponding sub-system.
BA03 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | システム間インターフェース設計 Inter-System Interface design
BA03-01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | ファイルレコード定義書（外部インターフェース）【BA03-01#02】 File Record Definition | HiICS/GCS | - Define content of file used for communicating between service if any. - Input: + Screen design (used to understand when the file will be send/receive from/to a service) + Use case (to understand the business for communicating between services) + Working flow (to understand what is the factor using the corresponding File Record)
BA04-01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | 通信メッセージ定義書【BA04-01#02】 Communication Message Definition | HiICS/GCS | - Define message content used for communicating between service if any
BA04-01#03 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | サービスインターフェース仕様書【BA04-01#03】 Service Interface Specification | HiICS/GCS
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | ビジネスプロセス詳細設計 Business Process Detail Design | HiICS/GCS
AA04-01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | ビジネスプロセス図（ＳＯＡ）(詳細)【AA04-01#01】 Business process diagram (SOA) | HiICS/GCS | - Define the relationship among service inside a business process, and business process with external services - Input: + Use case + ER diagram + Work flow - How to: + Based on information in Use Case document, we can know how many sub-component and their relationship based on 要素機能 information, and how many external service which Process Business contact with. + In use case document, it just say that group of data it will take only. We need to check ER diagram and Work flow, 情報システム関連図 to understand how many data will be transfered and its definition. - Output: + The relationship between business one process diagram and one sheet in User case document is 1-1. + Only the detail processes of corresponding component are described, another component processing content will be handled in their corresponding part. | - To handle the case in which the Business Flow in Excel is too long. We need to: + Check UseCase document to identify how many Sub-component in that corresponding Business Process + Prepare template, + Then copy to new page for template preparation. - Each send process has one receive process - One use-case includes some functionals defined in System functional list (BA document: BA02_xx_04_システム機能詳細一覧表_カーロケ.xlsx) - システム -> the business process itself, アクター: relating service (external actor).
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | 部品開発 (Componentization Design) | HiICS/GCS | - The purpose of this design document is to design component which composed the whole system. (Reusable component)
AA05-01#01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | システム部品一覧表【AA05-01#01】 List of System's Component | HiICS/GCS | - List of all system component
AA05-01#05 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | チェック・編集部品定義書【AA05-01#05】 Data check・Editing component definition | HiICS/GCS | - List of component which used to check the communication data between service - Input material: システム間インターフェース設計 + Message List + File record definition + Service interface => Based on above document, we will see what we need to check
AA05-01#06 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | ドメインチェック・編集仕様書【AA05-01#06】 Domain Check・Editing Specification | HiICS/GCS | - This document is used for checking domain of data (which used for communicating between services). - Domain of data can be taken from Data list document - Domain means the group information for each data + We need to define what we need to check on that group
AA05-02#06 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | API仕様書（共通部品）【AA05-02#06】 API specification (common part) | HiICS/GCS | - API specs template is not defined by HIPACE template, HiICS will create a Excel template for it to describe API (input, output, processing overview)
BA02-04#01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | メッセージ一覧表【BA02-04#01】 Message list | HiICS/GCS | - This document will be created simultaneously with Message Definition document in System Interface design by adding new message to the list if it doesn't have, use it if already have.
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | データ項目辞書運用 (Data dictionary) | HiICS/GCS
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | データ項目一覧表 Data definition list | HiICS/GCS | - For this time development, this document will be used for reference all Data used in system as well as 単語辞書 document - This document is updated simultaneously with ER document, message list, domain list
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | Ｄ層コンポーネント設計 (Data layer Design) | HiICS/GCS
AA07-02#01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | Ｄ層クラス・メソッド一覧表【AA07-02#01】 Class・Method List | HiICS/GCS | - This document define SQL statement used in the corresponding component. - Output: + SQL statement necessary for corresponding processing defined in SOA (AA) document - Input: + SOA (AA) document: to check which process need to have SQL definition. The name of process will be described in sheet "AA07-02#01_D層インタフェース一覧表（メソッド）" column 処理内容 and 論理名. + ER diagram, Entity List (BA) document for Database definition. + Message Interface (AA) document for which data will be transfered among sub-components. + BA07_02_01_システム機能詳細・エンティティ関連図(CRUD図)_カーロケ.xlsx -> Relationship table show which entity will be involved for each functional. | - Mapping relationship between D層インタフェース一覧表（DAO） and D層インタフェース一覧表（メソッド）sheet is 1-1. - The target table in SQL statement can be abstract Numeric name which represent multiple table in real database. - How many table will be envolved, we need to understand the nature/semantic of target system.
AA07-02#05 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | 処理・テーブル関連図（CRUD図）【AA07-02#05】 Processing・Table Relationship Diagram | HiICS/GCS | - This document define for a service, how many functional available in Functional layer relating to database access, and for each functional what is the target database table it will CRUD and the order of CRUD
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | Ｆ層コンポーネント設計 (Functional Layer Design) | HiICS/GCS
AA08-02#01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | F層クラス図【AA08-02#01】 Class Diagram | HiICS/GCS | - This document describe the class diagram of Functional layer. - It include the relationship between function layer, data access layer and relationship with service in business process + Which business process trigger the function in functional layer + Each function in functional layer will use data from DB through Database Access layer.
AA08-02#02 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | シーケンス図【AA08-02#02】 Sequence Diagram | HiICS/GCS | - This document describe the sequence diagram of each method in Functional layer. + Class name, functional name + And its sequence diagram
BA02-03#04 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | システム機能詳細一覧表【BA02-03#04】 System Functional Detail List | HiICS/GCS | - List of all functional in sub-system, and its related RQ id.
| Design Specs | Input for Offshore, Output for Onsite | In-Progress | バッチ設計 (Patch design) | HiICS/GCS | - Job is corresponding with Service Item in System Functional layer diagram.
AA10-01#01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | ジョブフロー図【AA10-01#01】 Job Flow diagram | HiICS/GCS | - This file describe the Job flow for each data in database when it run in Patch job inside Database server. + Which data table will be the target data. + Which process will process that data => Process overview - Input: + 01_BA\01.打合せ（履歴管理）\02_カーロケ\02_ジョブフロー定義\BA03_01_01_ジョブフロー図(概要)\BA03_01_01_ジョブフロー図(概要)_カーロケ.xlsx => Overview of all job flow in system and it's relationship overview. The data in this diagram is abstract data, so that for ジョブフロー図, we need to check with ER diagram, to see which data will be involved. + 01_BA\01.打合せ（履歴管理）\02_カーロケ\02_ジョブフロー定義\BA03_01_03_ジョブフロー一覧表\BA03_01_03_ジョブフロー一覧表_カーロケ.xlsx => List of all job in Car Location system, Detail information for each Job. + 01_BA\01.打合せ（履歴管理）\02_カーロケ\05_論理データモデルの作成 => Use to check for each data in Job flow, which data table will be involved. - Output: + The job flow diagram will define detail how many job will be available for one big Job group in ジョブフロー図(概要) document. - In some special cases, there is a possibility that this job flow diagram has only one job. + For each job flow, need to define in general: - It's input - It's duty - The target database system
AA10-02#01 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | ファイルレコード定義書【AA10-02#01】 File Record Definition | HiICS/GCS | - This file content is same with File Record Definition for interface between Process Business, System, but this file is for Patch processing. - For this time development, there is no file which is need to be processed by Patch Job. So that for Car Location, we don't need to create this kind of document for this time development.
AA10-02#02 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | ジョブステップ定義書【AA10-02#02】 Job Step Definition | HiICS/GCS | - Detail job step information for each job in Job flow - Input: + ジョブフロー図【AA10-01#01】 - Job Flow diagram of each job. + BA03_01_03_ジョブフロー一覧表_カーロケ.xlsx => Detail overview information of each job. - Output: + This material will define the necessary steps to accomplish the flow information defined in Job Flow diagram
AA10-02#03 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | プログラム構成図【AA10-02#03】 Program Structure Diagram | HiICS/GCS | - Describe the structure of each job in which the relationship between Functional Layer and Data Acess Layer is described.
BA05-02#04 | Design Specs | Input for Offshore, Output for Onsite | In-Progress | 帳票レイアウト定義書【BA05-02#04】 | HiICS/GCS | - Describe the layout for Patch job partner at Client side.

## functional_list
# | ID | サービスアイテム名 | ID | 要素機能名
1 | 3-1-1 | 動態管理 | 3-1-1T010 | 車両動態受信
2 |  |  | 3-1-1T020 | PSD動態受信
3 |  |  | 3-1-1T030 | PSW動態受信
4 |  |  | 3-1-1T040 | IPR動態受信
5 |  |  | 3-1-1T050 | 他県動態受信
6 |  |  | 3-1-1T050 | 他県動態更新
7 |  |  | 3-1-1T050 | 他県動態履歴登録
8 |  |  | 3-1-1T060 | 動態送信
9 | 3-1-2 | 業態管理 | 3-1-2T010 | 車両業態受信
10 |  |  | 3-1-2T020 | 車両業態通知
11 |  |  | 3-1-2T030 | 業態変更指示受信
12 |  |  | 3-1-2T040 | 業態変更指示通知
13 |  |  | 3-1-2T050 | ペアリング情報受信
14 |  |  | 3-1-2T060 | ペアリング情報通知
15 |  |  | 3-1-2T070 | 事案送信要求受信
16 |  |  | 3-1-2T080 | 事案情報通知
17 |  |  | 3-1-2T090 | 緊配送信要求受信
18 |  |  | 3-1-2T100 | 緊配情報通知
19 |  |  | 3-1-2T110 | 車載緊急発報受信
20 |  |  | 3-1-2T120 | 車載緊急発報通知
21 |  |  | 3-1-2T130 | PSD緊急発報受信
22 |  |  | 3-1-2T140 | PSD緊急発報通知
23 |  |  | 3-1-2T150 | PSW緊急発報受信
24 |  |  | 3-1-2T160 | PSW緊急発報通知
25 |  |  | 3-1-2T170 | IPR緊急発報受信
26 |  |  | 3-1-2T180 | IPR緊急発報通知
27 |  |  | 3-1-2T190 | 車載緊急発報解除受信
28 |  |  | 3-1-2T200 | 車載緊急発報解除通知
29 |  |  | 3-1-2T210 | PSD緊急発報解除受信
30 |  |  | 3-1-2T220 | PSD緊急発報解除通知
31 |  |  | 3-1-2T230 | PSW緊急発報解除受信
32 |  |  | 3-1-2T240 | PSW緊急発報解除通知
33 |  |  | 3-1-2T250 | IPR緊急発報解除受信
34 |  |  | 3-1-2T260 | IPR緊急発報解除通知
35 |  |  | 3-1-2T270 | 近傍車両検索要求受信
36 |  |  | 3-1-2T280 | 近傍車両検索結果通知
37 |  |  | 3-1-2T290 | 対応車両検索要求受信
38 |  |  | 3-1-2T300 | 対応車両検索結果通知
39 |  |  | 3-1-2T310 | 事案要求可否設定受信
40 |  |  | 3-1-2T320 | 事案要求可否設定更新
41 |  |  | 3-1-2T330 | 緊急車両台数検索受信
42 |  |  | 3-1-2T340 | 緊急車両台数通知
43 | 3-2-1 | 画像受信 | 3-2-1T010 | 画像受信
44 |  |  | 3-2-1T020 | 画像保管
45 |  |  | 3-2-1T030 | 画像受信通知
46 | 3-2-2 | 画像送信 | 3-2-2T010 | 画像送信
47 | 3-3-1 | 映像受信 | 3-3-1T010 | 映像受信
48 |  |  | 3-3-1T020 | 映像保管
49 |  |  | 3-3-1T030 | 映像受信通知
50 | 3-4-1 | 大型表示連携 | 3-4-1T010 | 動態送信
51 | 3-4-2 | 交通管制連携 | 3-4-2T010 | 渋滞情報受信
52 |  |  | 3-4-2T020 | 渋滞情報送信
53 |  |  | 3-4-2T030 | 規制情報受信
54 |  |  | 3-4-2T040 | 規制情報送信
55 |  |  | 3-4-2T050 | 文字メッセージ情報受信
56 |  |  | 3-4-2T060 | 文字メッセージ情報送信
57 |  |  | 3-4-2T070 | 駐車場情報受信
58 |  |  | 3-4-2T080 | 駐車場情報送信
59 |  |  | 3-4-2T090 | 区間旅行情報受信
60 |  |  | 3-4-2T100 | 区間旅行情報送信
61 | 3-4-3 | 他県動態表示連携 | 3-4-3T010 | 他県動態受信
62 |  |  | 3-4-3T020 | 他県動態送信
63 | 3-5-1 | メンテナンス | 3-5-1T010 | 自県車両メンテナンス
64 |  |  | 3-5-1T020 | 他県車両メンテナンス
65 |  |  | 3-5-1T030 | 送信周期メンテナンス
66 |  |  | 3-5-1T040 | 閉局エリアメンテナンス
67 |  |  | 3-5-1T050 | 用途メンテナンス
68 |  |  | 3-5-1T060 | 業態メンテナンス
69 |  |  | 3-5-1T070 | 呼出所属名称メンテナンス

## TODO
No | Category | Sub_category | TODO | Deadline | Note | Status
1 | Off_shore_team | Information | - Need to prepare all kind of materials for test + Test specs from Checklist, Requirement Design, DB design, AD design + Test environment specs + Drivers, Stub for testing - Implementation: + Follow business process diagram (SOA), to understand the business for each UseCase. + Follow class diagram, sequence diagram and SQL definition for implementation. | -
2 | Onsite_team | Design | - Create design document for 動態管理 (Movement managament) functional | 2018-01-24
3 | Onsite_team & offshore_team | Development Preparation | Which DB access technology can be used instead of using Pro-C for better maintenance? + When data is changed + When request SQL is changed | ???
4 | Onsite_team & Off_shore_team | Estimation | - For data access to Oracle, we need to consider the Data Access layer in case of OCI or Pro*C. - Correction estimation for P and PT will be available when Sequence Diagram is finished. + All other estimation need to put assumption for its corresponding abstraction level. | 2018-01-24
5 | Onsite_team | Estimation | - Check with customer about how to run unit-test manually | 2018-01-14
6 | Off_shore_team | Development Preparation | - Preparation for period for P and PT of offshore team is 3.5 months. | ???
7 | Off_shore_team | Development Preparation | - Prepare how to use Pro*C to implement embedded SQL to manipulate DB with HIRDB/Oracle. - Get familiar with Redhat development environment (Official: Redhat Enterprise, Free: CentOS) | ???
8 | Onsite_team | Estimation | - Checking the productivity number and the condition for it. - For GCS: + We need to familiar with domain, system to understand what is correct, what is not. + Language gap => There is possibility that engineer misunderstanding the design document => Re-work and design explaination over-head + Development duration should be long enough in order to engineer can get familiar with development domain to cover low-productivity period at the beginning. But for this time development, it's only 3.5 -> 4.5 months => The productivity number need to be adjusted. - For C language: + The average productivity number for only P & PT period is about 1.8kl + For short time development, it's take time for engineer to familiar with system development rule. - Condition for high productivity number: + Familiar with domain, technology to realize design idea to source code. + Can easy understand the design document in detail - There is language gap, so that there is possibility that Vietnamese engineer can mis-understanding the design idea => over-head may be high. + Duration is long enough | 2017-12-17 | - Communication idea: + Although Vietnamese team can't adapt to high productivity number, due to lef-hand side's stuck. + But it's necessary to have a feasible productivity number which is accepted by Hitachi and can handle by Vietnamese team. + GCS team is listening to HiICS for the feasible productivity number to make project run smooth.
9 | Onsite_team | Development Preparation | - How to prepare HIRDB server to perform pre-project technology investigation | 2017-12-18 | - No need to prepare HiRDB server, because Oracle will be used. | DONE
10 | Onsite_team | Design | - Checking created design document (up to 2017/12/15, the Form layouts for file record relating functionals are done) + z:\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\02_システム間インターフェース設計\BA03_01_02_ファイルレコード定義書（外部インターフェース）\PLGAS_BA03_01_02_ファイル・レコード定義書(外部インタフェース)_カーロケ.xls + z:\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\09_バッチ設計\BA05_02_04_帳票レイアウト定義書\BA05_02_04_帳票レイアウト定義書_カーロケ.xlsx + z:\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\09_バッチ設計\BA05_02_04_帳票レイアウト定義書\ => External Service Interface | 2017-12-15 | - Check to see whether programmer, designer can understand the document and make the program, design consistent between document.
11 | Onsite_team | Estimation and development prepration | - Confirm that does on-site team has test server to test the C program on linux | 2017-12-20 | - Hamatani-san will prepare the Redhat VM machine for testing | DONE
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37

## temp (hidden)
Car | Contents
- Based on material 【別紙】次世代通信指令 ＡＰＰ開発 HIPACE WBS作業内容概要.pdf, for Unit Test the output material is as following: + ドライバ・スタブプログラム + テストデータ + 打鍵シート（P層） + プラグラムチェックリスト (P/F/D バッチ) + チェックリスト観点マップ + ソースプログラム + DDチェックリスト + バグ管理表 + 仕様管理表 + プログラム変更表 + カバレージ情報 + 単体テスト実施報告書 + プログラム一覧表 The base documents are アプリケーションテスト計画・設計 and 詳細設計書. The question is who will create アプリケーションテスト計画・設計 and what are the target output document for unit test?
In RP11_02_01_制約条件一覧表.pdf material, there is required index for 業務切替え時間 of カーロケサーバ, what is 業務切替え時間 mean?
In RP05_01_04_業務機能階層図_170829t8.pdf material there are required functional for Car Location server as following: + PSD端末及びPSW端末から受信した動態情報を登録する。 + 他県車載端末から受信した動態情報を登録する。 + PSD端末とPSW端末がペアリング設定されている場合、動態をペアリング状態で管理する + 指定したPSD端末及びPSW端末に対してシステムロック及びロック解除を行う。 Based on above functional, Car Location server will directly contact with PSD, PSW, built-in device on car in other prefecture. But based on current design information, there are PSD system, other Prefecture's Car Location system and Car Location just directly contact to them, doesn't connect directly with PSD, PSW, car from other prefecture. Is our understanding correct? In that case, does RP material will be updated in future for consistent?

## Other_component_overview
Category | Service Component | Service Item | Service Functional overview | Processing Type | Note
- Common system has total 83 child functionals under 20 categories
Common | 1. 利用者認証機能 | 利用者情報管理 | 利用者情報の登録・削除を行う。 | Online
|  | 利用者情報検索 | 利用者情報を検索する。 | Online
|  | 利用者情報参照 | 利用者情報を参照・表示する。 | Online
|  | 利用者認証 | 生体認証またはＩＤ認証によりシステム利用者の認証を行う。 | Online
| 2. 状態監視機能 | 状態監視 | 各装置の運用状態（他装置との接続状態や端末の稼働状態）を監視する。 また、運用状態の変更時に他装置への通知を行う。 | Online
| 3. 画像管理機能 | 画像管理 | 画像情報の登録・削除を行う。 | Online | - Whether EMB team will handle this or not?
|  | 画像連携 | 警察車両・PSD/IPR端末などとの間で画像情報の送受信を行う。 | Online | - Whether EMB team will handle this or not?
|  | 画像検索 | 画像情報を検索する。 | Online | - Whether EMB team will handle this or not?
|  | 画像参照 | 画像情報を参照・表示する。 | Online | - Whether EMB team will handle this or not?
| 4. 映像管理機能 | 映像管理 | 映像情報の登録・削除を行う。 | Online | - Whether EMB team will handle this or not?
|  | 映像連携 | 警察車両などとの間で映像情報の受信を行う。 | Online | - Whether EMB team will handle this or not?
|  | 映像検索 | 映像情報を検索する。 | Online | - Whether EMB team will handle this or not?
|  | 映像参照 | 映像情報を参照・表示する。 | Online | - Whether EMB team will handle this or not?
|  | ライブ映像管理 | ライブ映像の配信状況を管理する。 | Online | - Whether EMB team will handle this or not?
|  | ライブ映像参照 | ライブ映像情報を参照・表示する。 | Online | - Whether EMB team will handle this or not?
| 5. 業務制御機能 | 業務制御 | 通信指令システムのアプリ起動や停止を制御する。 また、アプリのバージョン管理や更新アプリの配信などを行う。 | Online
| 6. マスタメンテナンス | マスタメンテナンス | 通信指令システムで利用するマスタファイルの作成や更新を行う。 | Online
| 7. 統計機能 | 統計 | 各種情報を集計し、統計帳票を出力する。 | Batch
| 8. 印刷機能 | 印刷 | 各種帳票、画像やハードコピーの印刷を行う。 | Online
| 9. 受信情報管理機能 | 受信情報管理 | 各種情報更新受信時、受信情報の概要表示を行う。 また、情報受信時のアラーム鳴動や受信情報の履歴管理などの支援を行う。 | Online
- Map system has total 173 child functionals under 14 categories
Map | 1. 基本機能 | 地図表示 | 地図上に各種情報を表示する。 | Online
|  | 地図検索 | 住所や目標物などの条件で地図上に表示する場所を検索する。 | Online
|  | メンテナンス | 地図システムで利用するデータの編集を行う。 | Online
|  | 印刷 | 地図を印刷する | Online
| 2. 連携機能 | 事案連携 | 通報聴取内容からの地図表示や地図からの場所特定などを行う。 | Online
|  | 緊配連携 | 地図上に緊配情報や配備箇所一覧を表示する。 | Online
|  | 車載連携 | カーロケシステムより取得した各端末の動態情報を、地図上に表示する。 | Online
|  | PSD/PSW/IPR連携 | カーロケシステムより取得した各端末の動態情報を、地図上に表示する。 | Online
|  | 画像連携 | 地図上に画像情報を表示する。 | Online
|  | 映像連携 | 地図上に映像情報を表示する。 | Online
|  | 災害情報ハブ連携 | 災害情報（災害、被害、交通、ライフライン、通信、画像・映像）を地図上に表示する。 | Online
|  | 交通管制連携 | 交通状況情報を地図上に表示する。 | Online
|  | Ｎヒット連携 | Ｎヒット情報を地図上に表示する。 | Online
|  | Ｓヒット連携 | Ｓヒット情報を地図上に表示する。 | Online
- Car Location system has total 225 child functionals 8 big functionals -> 22 categories -> 225 child functionals
Car | 1. 動態管理機能 | 動態管理 | 警察車両およびPSD/IPR端末の動態情報を受信・管理し、地図システムへ送信する。 | Online + Batch
|  | 業態管理 | 警察車両およびPSD/IPR端末の業態情報を受信・管理し、地図システムへ送信する。また、警察車両に対する業態変更を指示する。 | Online + Batch
| 2. 画像連携 | 画像受信 | 各車両より画像情報を受信し、共通システムへ中継する。 | Online
|  | 画像送信 | 共通システムからの画像送信を受け、各車両へ画像情報を送信する。 | Online + Batch
| 3. 映像連携 | 映像受信 | 各車両より映像情報を受信し、画像サーバへ中継する。 | Online
|  | ライブ映像連携 | 共通システム、各車両間のライブ映像情報を中継する。 | Online
| 4. 外部連携 | 大型システム連携 | 車両動態情報が更新された場合、動態情報を大型表示システムに転送する。 | Online
|  | 交通管制連携 | 交通管制システムから交通管制情報(VICS)を受信する | Online + Batch
|  | 他県動態表示連携 | 車両動態情報が更新された場合、動態情報を他県動態表示に転送する。 | Online
|  | 認証連携 | 車載装置からの認証を認証サーバと連携する | Online
| 5. メンテナンス | 自県車両メンテナンス | 自県車両マスタのメンテナンスをする | Online
|  | 他県車両メンテナンス | 他県車両マスタのメンテナンスをする | Online
|  | 送信周期メンテナンス | 送信周期情報のメンテナンスをする | Online
|  | 閉局エリアメンテナンス | 閉局エリア情報のメンテナンスをする | Online
|  | 用途メンテナンス | 用途マスタのメンテナンスをする | Online
|  | 業態メンテナンス | 業態マスタのメンテナンスをする | Online
|  | 呼出所属名称メンテナンス | 呼出所属名称マスタのメンテナンスをする | Online
|  | マスタ更新通知 | マスタを更新する | Online
|  | 事案要求可否設定 | 事案要求可否を設定する | Online
| 6. 業務制御 | 業務制御 | 業務状況を制御する | Online
| 7. 統計機能 | 統計 | 統計情報を管理する | Online + Batch
| 8. 災害機能 | 災害 | 災害情報を管理する | Online

## Document_relationship
- Document relationship can be checked in following material
+ 【別紙】次世代通信指令 ＡＰＰ開発 HIPACE WBS作業内容概要.pdf
- Important document
|  | + z:\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\07_Ｆ層コンポーネント設計\BA02_03_04_システム機能詳細一覧表\BA02_03_04_システム機能詳細一覧表_カーロケ.xlsx |  |  | - List of all functional in the system
No | RQ | BA | AA | AD | Meaning | Relationship
|  | Document: BA02_03_01_ユースケースシナリオ_アプリ設計作業_3-1-1-1_動態管理.xlsx Sheet: ユースケースシナリオ(動態履歴送信) | Document: 311_AA04_01_01_ビジネスプロセス図(SOA)(詳細)_動態管理.xlsx |  | - Cover following functional in BA02_03_04_システム機能詳細一覧表_カーロケ.xlsx document + 動態履歴を検索する + 動態履歴検索結果を地図システムへ送信する

## 資料を確認する質問
No | Document | Question | Answer | Status
1 | 通信メッセージ定義書、サービスインターフェース | PLAAはなにを表しますか？ | P：次世代通信指令システム（システム名） L：カーロケ（サブシステム名） A：動態管理機能（コンポーネント名、A,B,C…) A：動態管理（サービス名、A,B,C,…) | Closed
2 | HIPACE WBS作業内容概要 | 最新確認テストはどういうテストですか？ | 並行運転となります。 現行システムと今回作成する新システムの連動試験です。 | Closed
3 | チェック・編集部品定義書 | ①チェック・編集部品定義書を作成するためのインプット資料はどの資料でしょうか？ ②エラーメッセージ一覧はどこに管理しておりますか？ ③チェック・編集の処理の引数は三つ以上の場合はどう記載すればよいですか？そのときデータ型の列はどの引数の型を記載すれば良いですか？ | ①ビジネスプロセス図と通信メッセージ定義書から、各項目におけるチェック、編集を読み取り、記載します。 ②メッセージ一覧で管理します。 ③３つ以内となるように設計する方針としますが、確認します。 | Open
4 | ドメインチェック・編集仕様書 | ①単語辞書はどこに管理しておりますか？ ②ドメインという言葉はこのプロジェクトにてどんなことを表しますか？ ③P層、F層、D層を判断する根拠はなにですか？ | ①今回はデータ項目一覧を単語辞書とします。 ②データ項目のグループを表します。 ③画面表示に使用するならP層、データベースに使用するならD層、I/Fや内部処理に使用するならF層となります。 | Open
5 | API仕様書（共通部品） | 現在API仕様書（共通部品）フォルダにてサンプル及び今回のフォーマットはありませんので、再度確認していただけないでしょうか？ | F層メソッド詳細設計書のフォーマットを使います。 | Closed
6 | メッセージ一覧 | メッセージ一覧表を作成するために部品のチェック・編集の設計資料に基づいて作成しますか？それともどの処理を説明する資料に基づいて作成しますか？ | チェック・編集の設計資料を作成しながら、担当者が記入していきます。メッセージ一覧の作成担当は各チェック・編集定義を作成した人となります（複数人がこのメッセージ一覧を作成します）。 | Open
7 | D層インタフェース一覧表 | ① DB情報（テーブルの定義, フィールド名、フィールドの値等)はどこに確認でしょうか？ ② 備考列にてSQLステートメントの目的を記載しておりますが、その目的はどこから判断しますか？ | ①現状ER図のみです。 ②確認します | Open
8 | ”処理・テーブル関連図（CRUD図）”の”PLA_動態管理機能” | サービスアイテム名はSOA資料から抽出することを理解しておりますが、あっていますか？ | 正しくは(BA)システム機能詳細一覧を参照して作成となります。 | Open
9 | ”F層クラス図”の”F層クラス” | サンプルにて二つ資料: ”F層クラス図_SOA適用開発”と”F層クラス図_アプリ設計作業”がありますが、どちらもF層クラス図ですので、どのサンプルを利用しますか？ | 実際に作成するフォーマットはExcelファイルになります。 どちらかのサンプルを参照するのであれば、「アプリ設計作業」を参照してください。 | Open
10 | ”Ｆ層コンポーネント設計”の”シーケンス図” | サンプルフォルダにて二つサンプル”シーケンス図_SOA適用開発”と”アプリ設計作業”がありますので、どうちらもコンポーネント設計のシーケンス図ですが、どのサンプルを利用しますか？ | 実際に作成するフォーマットはExcelファイルになります。 どちらかのサンプルを参照するのであれば、「アプリ設計作業」を参照してください。 | Open
11 | ”Ｆ層コンポーネント設計"の”システム機能詳細一覧表” | この資料はBA段階ですでに作成されたので、AA段階にて参照するだけと認識しておりますが、合っていますか？ | 異なります。 BAで作成した段階では一番右列のメソッドが未入力です。 AAで作成した仕様書を参照し、メソッドを記入する工程となります。 | Closed
12 | ”バッチ設計"の”ジョブフロー図” | ジョブフロー図を作成するためにどの資料が必要かどうかを判断するためにどの設計情報を確認すれば良いですか？ | BAでのジョブフロー一覧、ジョブフロー図（概要）がベースとなります。 詳細を書くために、D層メソッド等の仕様書を使用します。 | Open
13 | ”バッチ設計"の”ファイルレコード定義書” | この資料は”ファイルレコード定義書（外部インターフェース）”と同様にパッチ処理用の資料であることを理解しておりますので、あっていますか？ | ファイルレコード定義書（外部インターフェース）は、インターフェースとして使用するファイル定義書で、こちらはバッチファイルで使用するファイルを記載するものです。 現時点、バッチ処理にてファイル出力は無い想定ですので作成枚数０枚と想定しています。 | Open
14 | ”バッチ設計”の”ジョブステップ定義書” | この資料はジョブフロー図の各ジョブの詳細情報を記載することを理解しておりますが、合っていますか？ | あってます。 | Closed
15 | ”バッチ設計”の”プログラム構成図” | この資料は各ジョブのプログラム構成（F層とデータベースアクセスの関係）を記載することを理解しておりますが、合っていますか？ | あってます。 | Closed
16 | 帳票レイアウト | 帳票レイアウトは参照としてはどの資料を参照すればよいですか？ | 既設帳票レイアウトから作成します。 | Closed
17 | ビジネスプロセス図（ＳＯＡ）(詳細)【AA04-01#01】の 動態管理 (パワーポイントバージョン) | 現在は以下の資料を作成してみましたので、ご確認のほどお願いいたします： \\app01\\00_APP_project\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\03_ビジネスプロセス詳細設計\AA04_01_01_ビジネスプロセス図（ＳＯＡ）(詳細)\GCS\311_AA04_01_01_ビジネスプロセス図(SOA)(詳細)_動態管理.pptx | 確認しました。この記載レベルで問題ありません。 | Closed
18 | ビジネスプロセス図（ＳＯＡ）(詳細)【AA04-01#01】の 動態管理 (エクセルバージョン) | 現在は以下の資料を作成してみましたので、ご確認のほどお願いいたします： \\app01\\00_APP_project\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\03_ビジネスプロセス詳細設計\AA04_01_01_ビジネスプロセス図（ＳＯＡ）(詳細)\GCS\311_AA04_01_01_ビジネスプロセス図(SOA)(詳細)_動態管理.xlsx | 確認しました。この記載レベルで問題ありません。 詳細の記載方法が12/13AM時点でまだありませんので、 わかり次第連絡いたします。 | Open
19 | ジョブフロー定義書・図 | ジョブフローの中にデータベースを定期的にアクセスすることですが、データベースにアクセスする際にロックされているかどうかを確認するためのロック情報（セマフォーリスト等）をどこに管理して、定義されますか？
20 | ジョブス図とジョブステップ図 | 例として以下の資料を動態管理-未受信処理のジョブに対してジョブ図とジョブステップを作成いたしましたので、ご確認のほどお願いいたします： \\app01\\00_APP_project\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\09_バッチ設計\AA10_01_01_ジョブフロー図\GCS\AA10_01_01_ジョブフロー図_カーロケ.xlsx \\app01\\00_APP_project\01_document\02_AA\01.打合せ（履歴管理）\02_カーロケ\09_バッチ設計\AA10_02_02_ジョブステップ定義書\GCS\AA10_02_02_ジョブステップ定義書_カーロケ.xlsx |  | Closed
21 | サービスインタフェースとファイルレコード定義資料について | 現在定義されるサービスインタフェース資料の中に黄色・グレー色を追加している項目に対して黄とグレーの意味を説明して頂けないでしょうか？
22 | 画像サーバについて | 各車両より映像情報を受信し、画像サーバへ中継する機能の画像サーバの担当チームはどのチームになりますか？ |  | Closed
23 | サーバのデータベースについて | カーロケサーバのデータベースは正式的にOracleを使うようになりますか？HiRDBに関しては使わないでしょうか？ |  | Open
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48